## Thursday(25.9)
To Do	Owner	Status
Setup GIT in all laptops	Arya	DONE
Project Requirements Doc – create	Everyone	DONE
ER Diagram	Everyone	DONE
Class Diagram	Everyone	DONE

## Friday(26.9)
To Do	Owner	Status	Soft Deadline

Set up REST API for EchoTest	Abhinav	Completed	0.5 day
Set up GUI for EchoTest	Arya	Completed	0.5 day
Create JAVA unit testing cases	Priya	Partially done	1 day
Create WPF unit testing cases	Arya	Incomplete	1 day
Prepare SP500 database	Nipun	Completed	0.5 day
Integrating the data	Nipun	Completed	1 day
Create entity beans	Krishma	Completed	1 day
Define timely-trends method	Apurva & Priya	Partially done	1 day
Define average deviations method	Abhinav	Incomplete	1 day