## Thursday(25.8)
To Do	Owner	Status
Setup GIT in all laptops	Arya	DONE
Project Requirements Doc – create	Everyone	DONE
ER Diagram	Everyone	DONE
Class Diagram	Everyone	DONE

## Friday(26.8)
To Do	Owner	Status	Soft Deadline

Set up REST API for EchoTest	Abhinav	Completed	0.5 day
Set up GUI for EchoTest	Arya	Completed	0.5 day
Create JAVA unit testing cases	Priya	Partially done	1 day
Create WPF unit testing cases	Arya	Incomplete	1 day
Prepare SP500 database	Nipun	Completed	0.5 day
Integrating the data	Nipun	Completed	1 day
Create entity beans	Krishma	Completed	1 day
Define timely-trends method	Apurva & Priya	Partially done	1 day
Define average deviations method	Abhinav	Incomplete	1 day

## Saturday(27.8)
To Do	Owner	Status	Soft Deadline

Discuss With Braun:
1.Where to store database?
2.How to share Java Eclipse Project?

Upload Big database	Nipun	Alternate solution

Sharing java Project		Solved
Storing database		Solved

End-to-end	Abhinav and Arya	Partially completed(only json left)	0.5 day

## Sunday(28.8)
To Do	Owner	Status	Soft Deadline

Complete round-trip connection	Priya and Arya	Completed	1 day
Time-trends analysis	Apurva	Completed	1 day
Deviation from averages	Abhinav	partially Completed	1 day
Adding categories in database	Nipun	Completed	1 day
Writing methods	Krishma	Completed	1 day
Added UI elements-basic graphs	Arya	Completed	1 day