## Thursday(25.9)
To Do	Owner	Status
Setup GIT in all laptops	Arya	DONE
Project Requirements Doc – create	Everyone	DONE
ER Diagram	Everyone	DONE
Class Diagram	Everyone	DONE

## Friday(26.9)
To Do	Owner	Status	Soft Deadline

Set up REST API for EchoTest	Abhinav		0.5 day
Set up GUI for EchoTest	Arya		0.5 day
Create JAVA unit testing cases	Priya		1 day
Create WPF unit testing cases	Arya		1 day
Prepare SP500 database	Nipun		0.5 day
Prepare Categories database	Nipun		1 day
Create entity beans	Krishma		1 day
Define timely-trends method	Apurva		1 day
Define average deviations method	Abhinav		1 day